## Quality of Ed
Objective | Action ID | Action Desc | Target Date | Actual Date | Notes | On track | Status | Owner
COVID-19 impact review including plan for future waves (CLARC) | 1 | CLARC Document Written | 2020-10-01 | 2020-10-01 |  | Green | In progress | Zoe
COVID-19 impact review including plan for future waves (CLARC) | 2 | Subject leadership Action Plans written to dovetail into SDP | 2020-10-01 | 2020-10-01 |  | Green | Complete | Laura, Alison, Phil
COVID-19 impact review including plan for future waves (CLARC) | 3 | RAG assess Subject leadership plans | 2021-02-01 | 2020-02-01 |  | Green | Complete | Laura, Alison, Phil
COVID-19 impact review including plan for future waves (CLARC) | 4 | RAG assess Subject leadership plans | 2021-05-01 |  |  | TBC |  | Laura, Alison, Phil
COVID-19 impact review including plan for future waves (CLARC) | 5 | Internal assessment plans | 2020-11-01 | 2020-11-01 |  | Green | Complete | All staff
COVID-19 impact review including plan for future waves (CLARC) | 6 | Trial Remote Learning via Teams | 2020-11-01 | 2020-11-01 |  | Green | Complete | All staff
COVID-19 impact review including plan for future waves (CLARC) | 7 | HT to attend well being 'Thrive' network sessions until March-21 | 2021-03-01 |  | x2 meetings attended so far- Nov-20 and Feb-21 | Amber | In progress | HT
COVID-19 impact review including plan for future waves (CLARC) | 8 | Set Remote Learning in place. | 2021-01-01 | 2021-01-01 | Remote learning in place for all classess. | Green | Complete | All Teaching and support staff
COVID-19 impact review including plan for future waves (CLARC) | 9 | Review the provision through the Review your Remote Learning guidance doc. | 2021-01-01 | 2021-02-01 | Audit completed and analysed. Remote learning offer on website | Green | Complete
COVID-19 impact review including plan for future waves (CLARC) | 10 | Parental surveys on Remote Learning provision- feedback used to improve provision offered to children | 2021-02-01 | 2021-02-01 | Staff given feedback on provision | Green | In progress | HT
COVID-19 impact review including plan for future waves (CLARC) | 11 | External moderation of writing standards to ensure that they are in line with National standards. Carried out by consultant | 2021-02-01 |  | Staff to upload work to the google drive to share | Amber | In progress | All teaching staff
COVID-19 impact review including plan for future waves (CLARC) | 12 | Covid Catch up premium to be used to support children who need extra support to catch up with learning | 2021-07-01 |  | Begun Oct-20 and ongoing. Groups/ individual children identified and supported. Ongoing evaluation as children return from second full lockdown | Amber | In progress | ZL/HF
Embed new curriculum and tailor non-core | 12 | Subject leadership monitoring ( see monitoring plan) | 2020-10-01 | 2020-12-01 | Some subject leadership minitoring has taken place but delayed after Jan-21 because of Covid. Governor monitoring has taken place. Staff has individual subject leadership plans that outline the progress they want their subjects to make | Amber | In progress | All teaching staff
Embed new curriculum and tailor non-core | 13 | Monitoring schedule amended because of delay due to Covid | 2021-02-01 |  | Monitoring schedule reviewed and added to. Revised timings because of Covid. | Green | Complete | HT
Embed new curriculum and tailor non-core | 14 | Evaluate monitoring plan for subjects | 2021-06-01 |  | Ongoing as per the Monitoring plan | Amber | In progress | all Teaching staff
Implement curriculum oversight and action plans | 15 | Subject leads to report to Governors | 2020-11-01 | 2020-11-01 |  | Green | Complete | All Teaching staff
Implement curriculum oversight and action plans | 16 | Subject leads to report to Governors | 2021-03-01 |  | Linked to work to be done with Locality Lead GW and staff meetings | Amber
Implement curriculum oversight and action plans | 17 | Subject leads to report to Governors | 2021-06-01
Bring school writing standards in line with national and above | 18 | Whole staff INSET on writing standards. | 2020-09-01 | 2020-09-01 |  | Green | Complete | All Teaching and support staff
Bring school writing standards in line with national and above | 19 | Read, Write, Inc phonics/ writing to be implemented | 2020-09-01 | 2021-09-01 | Training had to be resheduled because it was cancelled. ZL/AH to be retrained in March and rest of staff in September 21 | Amber | In progress | All Teaching and support staff
Bring school writing standards in line with national and above | 20 | External moderation of writing standards to ensure that they are in line with National standards. Carried out by consultant | 2020-11-01 | 2020-11-01 | This took place. Further training to take place with external consultant and Keystone Teaching school in Spring and Summer 21 | Amber | In progress | Teaching staff
Bring school writing standards in line with national and above | 21 | Subject leader to monitor writing standards. | 2020-11-01 | 2020-11-01 |  | Green | Complete
Bring school writing standards in line with national and above | 22 | Subject leader to monitor writing standards. | 2021-02-01 | 2021-02-01 | Done with children in school. Further analyis to be done when children return to school in March 21 | Amber | Complete | HT
Bring school writing standards in line with national and above | 23 | Staff to receive any necessary training based on the findings of moderation meetings. Reading training for each class teacher(s) Regular check in’s of standards | 2020-11-01 | 2020-12-01 |  | Green | Complete | All Teaching staff
Bring school writing standards in line with national and above | 24 | Staff to receive any necessary training based on the findings of moderation meetings. Reading training for each class teacher(s) Regular check in’s of standards | 2021-01-01 | 2021-06-01 | Ongoing moderation check in's throughout the rest of the school year | Amber | In progress
Bring school writing standards in line with national and above | 25 | Staff to receive x2 days INSET training for R, W, I | 2020-06-01 | 2021-09-01 | Rescheduled because cancelled due to Covid | Amber | In progress | All Teaching and support staff
Subject leader development | 26 | Engagement in 2nd year of East Midlands Maths hub | 2021-06-01 |  | Various meeting dates | Green | In progress | AH
Subject leader development | 27 | English and Maths Small School’s project. | 2020-11-01 | 2020-11-01 | Maths project had to be stopped due to lack of capacity. January meeting was resheduled and a new meeting scheduled for Feb-21. Subsequent ones will be booked. | Amber | In progress | ZL
Subject leader development | 28 | Teaching staff to learn more about subject leadership and to prepare for 'Deep Dives' in subjects | 2021-03-01 |  | Staff meeting scheduled for Feb-21 and follow up session on 'Deep Dives' for March-21 | Amber | In progress | All Teaching staff

## Behaviour Attitudes
Column1 | Action ID | Action description | Target date | Actual date | Notes | On track | Status | Owner
Focus on attendance and engagement - whole school and community | 1 | TS to attend attendance training- on how to monitor | 2020-10-01 | 2020-10-01 | Completed and advice acted on | Green | Complete | TS
Focus on attendance and engagement - whole school and community | 2 | Attendance monitored and reported on every half term | 2020-12-01 | 2020-12-01 | Completed | Amber | In progress | ZL/ TS
Focus on attendance and engagement - whole school and community | 3 | Attendance monitored and reported on every half term | 2021-02-01 |  | Not done due to lockdown will be restarted once school is reopened | Amber | In progress | ZL/TS
Focus on attendance and engagement - whole school and community | 4 | Attendance monitored and reported on every half term | 2021-03-01
Focus on attendance and engagement - whole school and community | 5 | Attendance monitored and reported on every half term | 2021-05-01
Focus on attendance and engagement - whole school and community | 6 | Attendance monitored and reported on every half term | 2021-07-01
Focus on attendance and engagement - whole school and community | 7 | CPOMS training to HT and Senior Administrator | 2021-02-01 | 2021-02-01 | HT to revisit CPOMS accounts and revise any 'open accounts' | Amber | Not started | Zl/TS
Evolving COVID-19 interim working model including ELSA support and ‘feeling safe in school’ | 8 | ELSA support to commence- 0.5 day a week. | 2020-09-01 | Ongoing | This has beeen operational since September 20 | Green | In progress | NL
Evolving COVID-19 interim working model including ELSA support and ‘feeling safe in school’ | 9 | HT and SENCO to attend 2 sessions of ‘Healthy Minds’ training. | 2020-12-01 | 2020-12-01 | Training attended and a well being day is to take place for the staff in the summer term 21 | Amber | In progress | ZL/NL
Evolving COVID-19 interim working model including ELSA support and ‘feeling safe in school’ | 10 | HT to become part of Thrive network – Keystone Teaching school. | 2020-11-01 | Ongoing | Through to Mar 21 | Green | In progress | ZL
Evolving COVID-19 interim working model including ELSA support and ‘feeling safe in school’ | 11 | ELSA support adapted to include children learning ‘remotely’ or ‘in school’ | 2021-01-01 | 2021-01-01 | ELSA is still operational eithe remotely or in person | Green | In progress | ZL/NL
Evolving COVID-19 interim working model including ELSA support and ‘feeling safe in school’ | 12 | Re-establish groups from Dec 20. Evaluate who needs support post lockdown | 2021-03-01
Evolving COVID-19 interim working model including ELSA support and ‘feeling safe in school’ | 13 | Monitor effectiveness of support- pupil/ parent questionnaire | 2021-05-01
Evolving COVID-19 interim working model including ELSA support and ‘feeling safe in school’ | 14 | Staff wellbeing session delivered | 2021-05-01
Review behaviour policies and status | 15 | Behaviour policy reviewed | 2020-12-01 | 2020-12-01 | Behaviour policy has been reviwed and approved by governors | Green | Complete | ZL/Govs
Review behaviour policies and status | 16 | Policy amended to include ‘blended ‘ model | 2021-01-01 | 2021-01-01 |  | Green | Complete | ZL/Govs
Review behaviour policies and status | 17 | Code of conduct issued for safe learning online | 2021-01-01 | 2021-01-01 | Sent to parents in Jan- 21 | Green | Complete | ZL/Govs

## Personal Devt
Objective | Action ID | Action Desc | Target Date | Actual Date | Notes | On track | Status | Owner
Re-establish pre-COVID-19 activities, tailor where necessary | 1 | Individual class activities to run e.g. SAT’s Booster Club, Football, Junior Road Safety Officers | 2020-09-01 | 2020-09-01 | These activitoes were reestablished in the Autumn term of 20. Howeverm they were suspended in Jan-20 and need re starting once school fully reopens | Amber | In progress | ZL and staff
Re-establish pre-COVID-19 activities, tailor where necessary | 2 | Set up Music Sessions to cover PPA with Lincolnshire Music Service | 2021-01-01 | 2021-01-01 | Successful setting up of the Lincolnshire Music Service working with Y2 to Y6 and covering PPA. Private music lessons offered in 5 instruments. | Green
Re-establish pre-COVID-19 activities, tailor where necessary | 3 | Re-offer private music lessons and those who want them through use of PP | 2021-01-01 |  | Readvertise private music lessons once school is fully open | Amber | In progress | ZL/KJ
Re-establish pre-COVID-19 activities, tailor where necessary | 4 | Premier Education ( sports) to deliver | 2021-01-01 | 2021-01-01 | Premier Education voach using lateral testing and coming into school to deliver sports for PPA cover | Green | Complete | ZL
Re-establish pre-COVID-19 activities, tailor where necessary | 5 | Review provision of what is offered to children | 2021-02-01
Re-establish pre-COVID-19 activities, tailor where necessary | 6 | Set up a school choir | 2021-03-01 |  | The plan is to start this as soon as possible upon reopening and using risk assessment
Focus on Resilience in pupils and staff | 7 | ZL to attend ‘healthy minds’ sessions on Wellbeing | 2020-12-01 | 2020-12-01 | Wellbeing day to be set up for staff | Amber | In progress | ZL/NL
Focus on Resilience in pupils and staff | 8 | Staff well being sessions | 2021-06-01
Prepare for “World View” developing ”Cultural Capital” | 9 | Staff to evaluate subject content in their curriculum areas | 2021-04-01 |  | Staff on the constant look out for how to enrich their subject and offer 'cultural capital'
Prepare for “World View” developing ”Cultural Capital” | 10 | Use of online resources to support online learning e.g. Online theatre, museum visits etc. | 2021-04-01 |  | On-going
Prepare for “World View” developing ”Cultural Capital” | 11 | GLOW project organised by the KYRA partnership culminating in a performance | 2021-07-01 |  | Glow partnership signed up for. Support found to be invaluable | Amber | In progress | ZL and staff

## Leadership
Objective | Action ID | Action Desc | Target Date | Actual Date | Notes | On track | Status | Owner
Stable roll (16 Y6) | 1 | Staff fully understand need to retain existing roll and to engage with prospective parents | 2021-01-01 | 2021-01-01 | Provisional Reception place applications are 11 first choice places. Parents and families have been shown around school after hours socially distanced. | Green | In progress | ZL and staff
Stable roll (16 Y6) | 2 | Use of Stay and Play Open Mornings at regular points in the Autumn term- these were postponed/ rearranged depending upon Covid. | 2020-09-01 | 2020-12-01 | More to be offered post lockdown and after the initial offer of places. | Amber | In progress | ZL and staff
Stable roll (16 Y6) | 3 | Individual appointments offered in person, remotely | 2021-04-01 |  | Following places being offered
Stable roll (16 Y6) | 4 | School video to be produced to promote the school- parents, children, staff, governors voice on video | 2021-03-01 |  | Contact has been made with contact who can produce the video and parents have volunteered to speak on the video | Amber | In progress | ZL/TS/SW
With Governors, update and communicate school vision | 5 | Vision created with all stakeholders and shared | 2020-09-01 | 2020-09-01 | Vision complete and SIAMS strands being analysed to see if they uphold this vision | Amber | In progress | ZL
With Governors, update and communicate school vision | 6 | Policies renewed as part of cycle to fit with the vision | Ongoing |  | Ongoing
Align staff performance management to strategic plan | 7 | Teaching and support staff performance managed | 2020-09-01 | 2020-10-01 | Initial appraisals held and mid year meetings completed. | Green | Complete | ZL/LL/AH/PH
Align staff performance management to strategic plan | 8 | Teaching and support staff performance managed | 2021-02-01 | 2021-02-01 | 2020-09-01 | Green | Complete | ZL and support staff
Align staff performance management to strategic plan | 10 | SDP shared with staff and governors | 2021-09-01 | 2021-09-01 |  | Green | Complete | ZL/Govs
Embed performance monitoring plan with Governors (OFSTED 2) | 11 | SDP progress review with governors | 2020-11-01 | 2020-11-01 |  | Green | Complete | ZL/Govs
Embed performance monitoring plan with Governors (OFSTED 2) | 12 | SDP progress review with governors | 2021-01-01 | 2021-01-01 |  | Green | Complete | ZL/Govs
Embed performance monitoring plan with Governors (OFSTED 2) | 13 | SDP progress review with governors | 2021-03-01
Embed performance monitoring plan with Governors (OFSTED 2) | 14 | SDP progress review with governors | 2021-05-01
Embed performance monitoring plan with Governors (OFSTED 2) | 15 | SDP progress review with governors | 2021-06-01
Embed performance monitoring plan with Governors (OFSTED 2) | 16 | Governors to monitor learning in school. Meeting with staff remotely | 2021-02-01 | 2021-02-01 | Governors have attended online lessons and met remotely with staff. Feedback to be given at Governor's meeting | Green | In progress | Zl/Govs

## Early Years
Objective | Action ID | Action Desc | Target Date | Actual Date | Notes | On track | Status | Owner
Continuous Provision/outdoor areas improvements with external support | 1 | Meet remotely with EYFS consultant Helen Rutherford to look at outdoor provision and to revisit after new surface has been fitted | 2020-10-01 | 2020-10-01 | Completed remotely and suggestions made. Reading advice given | Green | Complete | LL
Continuous Provision/outdoor areas improvements with external support | 2 | Meet remotely with EYFS consultant Helen Rutherford to look at outdoor provision and to revisit after new surface has been fitted | 2021-03-01 |  | Awaiting the completion of the outdoor area and setting up new area | Amber | In progress | ZL/LL
Continuous Provision/outdoor areas improvements with external support | 3 | New outdoor surface to be installed | 2021-02-01 |  | Due to be installed 24/02/21 | Amber | In progress | ZL/LL
Continuous Provision/outdoor areas improvements with external support | 4 | Monitoring of continuous provision | 2021-05-01
5
6
7
8
9
10

## Data
Owners | Zoe
Alison
Phil
Laura
Holly
Staff 1
Staff 2
Staff 3
Staff 4
Staff 5