## Slide 1: School Strategic Development Plan
November 2020
Truthfulness, Compassion, Respect , Forgiveness

## Slide 2: Introduction
This plan sets out the strategic goals and plans for All Saints Primary School Swinderby
The overall objective is to reach a level of ‘Outstanding’ in terms of OFSTED ratings
The plan contains a three year, strategic plan which sets out the roadmap to reach ’Outstanding’
There is a more detailed one year plan which describes the specific actions needed to deliver this stage
This is a three year rolling plan will be refreshed each year with a detailed plan developed for the coming year

## Slide 3: Input to the Planning
This plan is based on input from the Governing body, staff, Headteacher, Local Authority and previous OFSTED findings (2017)
The OFSTED findings were as follows
  Teachers set more challenging work for the more able pupils to increase the proportion of pupils who reach higher standards in maths
    Action complete, evidence would have been in 2020 SAT results.
    Monitor 2021 SAT results to confirm
  They include clear, measurable targets in the school’s plans for improvement so that the Governing body can use them to hold leaders to account
    In 2020-21 strategic plan
  Leaders provide the Governing body with more detailed and regular information about pupils’ progress
    Action complete

## Slide 4: Working Assumptions
This plan is based on the following assumptions which form the basis of planning.
If these assumptions change then the plan will be reviewed
The key assumptions are as follows
  KS1 and KS2 data will be required in 2020/2021
  KS1 and KS2 tests will be held as normal in 2021
  COVID-19 will impact school working through to July 2021 but not beyond at this stage
    Potential for local lockdown measures so need to be able to support children remotely ( See (CLARC document)

## Slide 5: Key Targets for 2020/2021
Whilst there are many areas of attention the following points will be our priority for this academic year
Recover from COVID and improve resilience
Embed new curriculum
Raise teaching and learning standards

## Slide 6: Strategic Development Plan - Three Year Plan
Improvement Areas | 2019-2020 Based on latest SEF | Year One 2020-2021 | Year Two 2021-2022 | Year Three 2022-2023
Overall Target Level | Requires Improvement | Good | Good | Outstanding
Quality of Education | Status: Requires Improvement Actions: New curriculum defined and implementation started Subject leaders in place Monitoring & assessment plans in place Writing identified as focus area | Target: Good Focus Areas: COVID-19 impact review including plan for future waves learning Embed new curriculum and tailor non-core areas Implement curriculum oversight and action plans Bring school writing standards in line with national and above Subject leader development Execute monitoring & assessment plans Execute independent Teaching and Learning Review | Target: Good Focus Areas: Curriculum interim review Focus on school wide subject training Review monitoring & assessment plan | Target: Outstanding Focus Areas: Plan curriculum refresh
Behaviour and Attitudes | Status: Good Actions: Attendance policy re-written and enforced New rewards and Houses COVID-19 emergency working model | Target: Good Focus Areas: Focus on attendance - whole school and community Evolving COVID-19 interim working model including ELSA support and ‘feeling safe in school’ Review behaviour policy and status | Target: Outstanding Focus Areas: Refresh of school values Focus on behaviour Focus on bullying including on-line safety | Target: Outstanding Focus Areas: Focus on attendance
Personal Development | Status: Good Actions: External events, sport, clubs, PGL, positions of responsibility COVID-19 curtailment of activities | Target: Good Focus Areas: Re-establish pre-COVID-19 activities, tailor where necessary Focus on Resilience in pupils and staff Prepare for “World View” and developing ‘Cultural capital’ | Target: Outstanding Focus Areas: Focus on “World View” Prepare for “Opportunities for Me” | Target: Outstanding Focus Areas: Focus on “Opportunities for Me”
Leadership and Management | Status: Requires Improvement Actions: Stable roll (lost 18 Y6) Strong engagement with community Improving staff capability via personnel changes Clearer staff accountability Updated Safeguarding processes | Target: Good Focus Areas: Stable roll (15 Y6) With Governors, update and communicate school vision Align staff performance management to strategic plan Embed performance monitoring plan with Governors (OFSTED 2) | Target: Good Focus Areas: Increase roll +5 (8 Y6) Review staff performance management approach Review safeguarding effectiveness | Target: Outstanding Focus Areas: Increase roll +10 (9 Y6) School strategy refresh
Quality of Education of Early Years | Status: Requires Improvement Actions: Reviewed EYFS planning External moderation of assessments | Target: Good Focus Areas: Continuous Provision/outdoor areas improvements with external support | Target: Good Focus Areas: Review pre-school provision | Target: Outstanding Focus Areas: TBC

## Slide 7: Year One Action Plan - Quality of Education
Objective | Description | Owner | Resources | Budget | Monitoring | Dates
COVID-19 impact review including plan for future waves (CLARC) | Assess impact from COVID on children’s progress. Review education provision that was provided. Complete CLARC review Assess children’s current status Prepare COVID resilience plan for future waves - use CLARC document | ZL | HT time | ZL time | HT - CLARC provided to locality lead HT - Report to Governors HT - Action plan tracking as required | Complete assessment in September
Embed new curriculum and tailor non-core | New curriculum in place but requires making tailoring Non-core areas still require embedding Subject leaders to check for delivery, coverage and impact | Subject Leaders | x1 day a term release- Autumn, Spring, Summer | ZL to cover | By Subject Leaders with Feedback to HT on findings as per Assessment & Monitoring plan. Tailoring demonstrated in planning. | Rollout starts Sep 2020 and runs for 2 years
Implement curriculum oversight and action plans | Following new curriculum rollout implement regular tracking meetings to ensure objectives are being met Implement reporting for HT and Governors from subject leaders Action plans to be written for all subjects by subject leads | Subject Leaders | x1 day a term release- Autumn, Spring, Summer | ZL to cover | HT and Chair of Governors to monitor Reporting to Governing Body | Initial set up October. Checkpoints with subject leads in Oct, Feb, June
Bring school writing standards in line with national and above | Resources purchased Introduce Read, Write, Inc. phonics scheme | AH | Work with English hub x1 day training in September for ALL STAFF | Training £1.5K | AH - Regular assessments defined in the Monitoring & Assessment plan | Training put on hold until November
Subject leader development | Maths and English subject leaders to take part in ‘Small Schools’ project Subject leads to deliver training to all staff Other options as COVID restrictions allow | Subject Leaders | Release days TBC Awaiting plans from the Teaching School | TBC | HT to monitor through performance management and subject leader reports | TBC (see note)
Execute monitoring & assessment plan | Rollout of monitoring and assessment plans previously defined Evaluate progress against the Monitoring Assessment documents | Head | Head Teacher time | ZL time | HT to monitor status against defined plan | Weekly targets defined in plan
Execute independent Teaching and Learning Review | Planned and agreed in 2019/20 Once review completed HT to work through findings and draw up detailed action plan to address areas of concern | ZL | Independent Assessor from LAAT Tamara Allen | £2K | Assessor report to be provided to HT and Governors HT - Action plan tracking as required | Earliest slot October/November subject to COVID controls

## Slide 8: Year One Action Plan - Behaviour and Attitudes
Objective | Description | Owner | Resources | Budget | Monitoring | Dates
Focus on attendance and engagement - whole school and community | Promoting attendance by all pupils Addressing COVID concerns affecting attendance Run ‘Engagement for Learning’ programme to remove barriers to learning | HT to lead All Staff supporting | x2 1 hour twilight sessions delivered from EP Team | Part of EP budget purchased for the year | Monitor attendance data each half term Use CPOMS process escalate urgent issues | Sessions in Oct/Nov Daily alerts Half termly monitoring
Evolving COVID-19 interim working model including ELSA support and ‘feeling safe in school’ | Initial working model around class bubbles defined and implemented Input to COVID resilience plan (ELSA) Define ELSA support, specifically to address COVID related issues | ZL NL NL | NL - 0.5 day a week to ensure support | Included in existing staff budget | ZL to have regular meetings with NL to track progress NL to monitor CPOMS for specific issues and trends | Start work in Sep Resilience plan complete in Sep On-going monitoring
Review behaviour policies and status | Review behaviour policy to ensure it meets needs current needs including COVID impacts | ZL with Teaching staff | Staff meeting time | Staff time | ZL to report to Governors on new policy | Start Sep Present to Governors in Oct

## Slide 9: Year One Action Plan - Personal Development
Objective | Description | Owner | Resources | Budget | Monitoring | Dates
Re-establish pre-COVID-19 activities, tailor where necessary | Re-establish positions of responsibility where possible compliant with COVID restrictions Re-establish extra-curriculum activities where possible | Staff members responsible for activities | Staff time | Staff time Consider additional expenditure where proposed by staff | Staff members to propose plans ZL to track progress via regular reports | Positions - Started in Sep
Focus on Resilience in pupils and staff | Develop COVID Resilience plan focusing on personal resilience Align with ELSA plans | NL to lead | Staff time | Consider additional expenditure where proposed by staff | ZL to monitor with NL | Nov
Prepare for “World View” developing ”Cultural Capital” | Long term activity to provide children with understanding of their place in the world Provide opportunities for pupils in culture, religion and places Update curriculum for rollout starting Sep 2021 | ZL | Staff time plus external support | TBC | ZL to monitor plan and report to Governors | Start in Easter 2021

## Slide 10: Year One Action Plan - Leadership & Management
Objective | Description | Owner | Resources | Budget | Monitoring | Dates
Stable roll (15 Y6) | Understand reasons for leaving over last 3 year. Implement exit interviews and reporting. Brief staff on expectations and link to loss of pupils Hold events and Stay-and-play (when possible) Initial marketing plan | ZL to lead All staff supporting | ZL time Governors Friends of School | £100 Aim to leverage good will | ZL to report on numbers (and changes) ZL to monitor predicted numbers for 2021 | Open days planned for 2020 (subject to COVID restrictions)
With Governors, update and communicate school vision | Work with Governing body to refresh the school vision Communicate this to stakeholders Update school development plan | Chair of Governors | Governors plus ZL | None | Track progress at Governor meetings | Run session at Governors meeting in September Aim to launch Jan 2021
Align staff performance management to strategic plan | All performance management plans amended to align with this plan | ZL | Staff time | None | ZL to report to Governors | Initial alignment in Sep 2020
Embed performance monitoring plan with Governors (OFSTED 2) | Plan already shared with Governors Will be monitored with RAG status | ZL | Governors plus ZL | None | ZL to report to Governors | Presented at Governor meetings

## Slide 11: Year One Action Plan - Quality of Education EYFS
Objective | Description | Owner | Resources | Budget | Monitoring | Date
Continuous Provision/outdoor areas improvements with external support | Work with external consultant to assess and develop outdoor area | LL and CH | Staff time and external consultant | £170 | LL report to ZL | Initial review October Review Feb / May

## Slide 12: Year Two High Level Plan - 2021-2022
Improvement Areas | Target Achievement | Improvement Areas | Notes
Quality of Education | Good | Focus Areas: Curriculum interim review Focus on school wide subject training Review monitoring & assessment plan | 
Behaviour and Attitudes | Outstanding | Focus Areas: Refresh of school values Focus on behaviour Focus on bullying including on-line safety | 
Personal Development | Outstanding | Focus Areas: Focus on “World View” Prepare for “Opportunities for Me” | 
Leadership and Management | Good | Focus Areas: Increase roll +5 (8 Y6) Review staff performance management approach Review safeguarding effectiveness | 
Quality of Education of Early Years | Good | Focus Areas: TBC | 
Target OFSTED Level - Good

## Slide 13: Year Three High Level Plan - 2022-2023
Improvement Areas | Target Achievement | Improvement Areas | Notes
Quality of Education | Outstanding | Focus Areas: Plan curriculum refresh | 
Behaviour and Attitudes | Outstanding | Focus Areas: Focus on attendance | 
Personal Development | Outstanding | Focus Areas: Focus on “Opportunities for Me” | 
Leadership and Management | Outstanding | Focus Areas: Increase roll +10 (9 Y6) School strategy refresh | 
Quality of Education of Early Years | Outstanding | Focus Areas: TBC | 
Target OFSTED Level - Outstanding

## Slide 14
Truthfulness, Compassion, Respect , Forgiveness