## Focus Areas
Introduction & Background
The School Development Plan has been written based on the four Ofsted categories of Quality of Education, Personal Development, Behaviour and Attiudes and Leadership and Management. The areas to focus upon have been decided through analysis (see Self Evaluation form). Where items are RAG rated as orange or red they create an action. In addition, the outcomes of the Teaching and Learning review carried out in June 2021 by the LAAT have given some additional actions. Subject leaders have worked on the Quality of Education section of the sEF and have produced action plans which have fed into the SDP . These plans can also be accessed separately. Each focus area has priorities, these are broken down into objectives and each objective has actions which have areas of responsibility and timescales linked to them. The majority of the focus is on Quality of Education and Leadership and Management. These actions are RAG rated as the time progresses and there are overall milestones to monitor progress at certain points. The purpose behind using a speadsheet is to enable live tracking to take place. This is underway. The whole plan is aso supported by the Monitoring/ Assessment schedule 2021-2022.
Consultants working with the School
Helen Rutherford Early years support
Catherine Caldwell to support with moderation
Anita Coupland sustaining year Maths hub
Leann Lynch subject Leadership

## Priority areas incl.objecti
Swinderby All Saints |  | 2021-2022
School Strategic Development Plan
OFSTED Area | PRIORITY | Objectives | Success criteria | by Dec | by April | by July
Quality of Education | QE1: To improve outcomes in reading so that they are above national, both in EXS or GDS | QE1:1 To ensure each member of staff sets challenging targets in reading to help them make good progress from their starting points | a) Staff can confidently talk about their child's target and how they will overcome barriers to meet it b) Staff have a clear understanding of where each child is at and what the child needs to do to succeed | Targets set by September, checked. Reviewed at pupil progress meeting November. Inteventions are used if required | Targets monitored March. | 100% of staff are able to discuss their child's end of year targets with the children's next teacher
|  | QE1:2 To ensure high quality phonics is taught daily | a) Daily R,W,I phonics is at least 'good' | All staff are delivering Read, Write, Inc phonics | 100% of phonics lessons are at least good | 100% of staff talk knowledgeably about their delivery of R,W,I
|  | QE1:3 To ensure high quality phonics resources are being used | a) Children are given access to high quality R,W,I resources | Read, Write, Inc respurces are fully in place |  | Evaulation of Read, Write, Inc resources ahead of Year 2 delivery
|  | QE1:4 To ensure staff are trained in the teaching of reading to a high standard | a) Staff are competent in the delivery of R,W,I and know where to go to if they need to find something out | All staff delivering R, W, I are trained and supported using individual training plan | Staff are confident with delivery of R W, I | 100% staff delivering R,W,I are delivering lessons that are at least good | Needs to continue across all of KS2
|  |  | b) Staff know how to deliver high quality reaading lessons | All staff have received 0.5 day's reading comprehension training and lessons observed demonstrate this knowledge is being used | Staff are confident in teaching reading
|  | QE1:5 To ensure children have access to a exciting and stimulating reading environment |  |  | 100% of staff can discuss their child's progress towards their targets | 100% of staff are able to discuss their child's end of year targets with the children's next teacher
|  | QE1:6 To ensure children have access to age appropriate reading texts | a) Children are reading high quality, challenging texts for their age and ability | All reading books are banded and match phonics scheme | Children reading high quality texts | 100% of children interviewed will talk animatedly about their reading
|  | QE1:7 To ensure the profile of reading is raised across the school | a) The love of reading is seen all around school | High quality reading is evident in all classrooms | Children talk about their reading | The lowest 20% of children in each class make good progress
Quality of Education | QE2: To improve outcomes in GDS in maths | QE2.1 To ensure staff fully understand what fluency looks like in maths. | a) Staff ensure that stretch and challenge is evident in all maths lessons delivered | Subject lead has observed stretch and challenge in each class | Staff understand fluency in lessons and this is observed in monitoring | % of GDS in assessments in line with national average
|  | QE2.3 To know that staff deliver high quality teaching in maths |  | Fluency in core maths evident in classrooms through extra teaching sessions | Children talk confidently about their maths in pupil interviews
Quality of Education | QE3: To improve outcomes in writing so that they are at least in line with national, both at EXS and GDS | QE3:1 To ensure each member of staff sets and understands their child's targets | a) Staff talk confidently of where they want each child to be in writing b) Staff routinely help children overcome barriers to making progress in writing | Pupil progress meetings have identified those on track and those who need extra support | 100% of staff can discuss their child's progress towards their targets | 100% of staff are able to discuss their child's end of year targets with the children's next teacher
|  | QE3:2 To ensure high quality writing is taught everyday | a) Writing is taught to at least a good level
|  | QE3:3 To ensure staff model and teach writing on a regular basis | a) Writing is seen to be modelled by teachers in class at least 3 times a week | Writing is seen being taught at least x3 times a week in 100% of the classes | Writing is seen being taught at least x4 times a week in 100% of the classes | Children talk about how they are taught how to write
|  | QE3:4 To ensure high quality resources are used | a)Children always have access to high quality writing materials
|  | QE3:5 To ensure writing is celebrated and its profile raised across school | a) Writing is celebrated and valued by ALL in school | The celebration of writing is evident in the classrooms | The celebration of writing is evident around school | The celebration of writing is spoken about by children
Quality of Education | QE4: To ensure that the curriculum is bespoke, cohesive and broad and balanced meeting the needs of the pupils | QE4.1 For subject leaders to ensure that their subject is part of a broad and balaced curriculum offer | a) Each curriculum area is well planned and led by subject leaders | All subject curriculum overviews/progression plans are in place on school website | Curriculum leaders have full knowledge of how their curriculum progresses from EYFS to Y6 | Subject leaders can articulate strengths and weknesses in their own subjects
Personal Development | PA1: To ensure that the curriculum is cohesive and broad and balanced meeting the needs of the pupils | PA1.1 Subject leaders to enhance opportunities for children alongside the curriculum areas | a) Subject leaders understand how their subject progresses from Yr to Y6 | All staff to have added school specific content to their curriculum
| PA2: Staff to understand how the SIAMS framework fits into the curriculum | PA2: Staff to understand the requirements of the SIAMS framework | a) Subject leaders talk in detail about the SIAM framework | Staff to know about SIAMS framework | Staff to have contributed to strands 1 and 2 | Staff to have contributed to Strands 3 and 4
Leadership & Management | LM1: To ensure subjects are led and well managed to deliver high quality education in all curriculum areas | LM1.1 To train and develop middle leaders within school able to lead their subject well | a) Subject leaders are trained and have ownership and acountability for their Subject Action Plans | All subject leads have led at least one staff meeting and taken part in one monitoring cycle | All subject leads have led a second staff meeting and taken part in one monitoring cycle | All subject leads know the strengths and weknesses in their subject
|  | LM1.2 To ensure all staff leading subjects are well trained and understand their roles and responsibilities | a)Staff know their subject well and advise on CPD for colleagues where necessary | Subject leads RAG rate their action plans | Subject leaders talk about the progress aginst their action plans | Subjects leaders discuss their next steps for their subjects
|  | LM1.3 To ensure all staff know how to monitor their subjects including the data and to act accordingly to improve outcomes | a) Staff talk knowledgably about the data around their subject and how to improve it | Subject leaders understand the data for their subject and can identify strengths and weaknesses | Subject leaders talk about the impact of any intervention/changes made | Subject leaders understand their data and can identify next steps
|  | LM1.4 To ensure all staff identify themselves and others training needs to enable them to deliver high quality teaching | a) Training needs are met ro ensure the highest quality offer is given to children
|  | LM1:6 To ensure that all staff keep themselves and others updated and aware of current evidence based practice within their subjects | a) Subject leaders have control of their subject and use current guidance to stay abreast of any changes within it using evidence based research
| LM2: To ensure that all classroom environments meet the needs of their pupils | LM2:1 To ensure that all classroom environments are age appropriate, bright and stimulating for the year group | a) Clasroom environments are bright and inviting and aspirational | All classrooms have a reading corner that is being used | 100% of corridors are bright | All work space areas are bright and inviting
|  | LM2: 2 To ensure that the EYFS environment meets the needs of the new EYFS currculum | a)The EYFS environment meets the needs of the children through evidence of continous provision | There is evidence of continous provision | Y1 children are making good progress within a classroom with continous provision
| LM3: To develop a self improvement model within school | LM3: To use the peer review process as a vehicle for self improvement | a) For the school and staff to be able to identify its own strengths and weaknesses | Peer Review cycle begun | Peer review cycle follow up meeting taken place | Peer Review cycle evaluateda and restarted
b) Staff talk aspirationally of targets for their pupils and for this language to be modelled by all
Non Ofsted area | NOA1: To increase the number of children on roll | NOA1:To explore the possibility of the school taking on Swinderby pre school and setting up an early years group | a) To become the school of choice | To know if the option is to be taken to the next stage | TBC | TBC
b)To know if the pre school are in agreement to become part of the school
| NOA2: To make a wider use of the outside environment | NOA2: To explore the option of Forest schools | a) Staff using the outdoors as a means of learning | Outdoor areas being used | Contact made with Forest Schools
| NOA3: To replenish whiteboards in the school |  | a) To factor replenishment into the school budget | Obtain a quote for the replacement of whiteboards in the school | Set budget 2022-23 with IT replenishment in mind

## Actions
Priority | Objective | Action Ref. | Action | Lead person | Start date | Finish date | Costs | Monitoring | RAG Rating | Narrative/comments
QE1 | 1.1 | 1.1.1 | Staff set individual targets for each child | LL,AH,HF,HC | 2021-09-03 | 2021-09-17 | 0 | HT via the G drive | Complete
|  | 1.1.2 | Staff to RAG rate reading in class and allocate reading support according to need. The lowest 20% need extra support | LL,AH,HF,HC | 2021-09-01 |  |  |  | Complete
|  | 1.1.3 | Staff identify PP children in class and plan for teaching of them | LL,AH,HF,HC | 2021-09-01 | 2021-09-17 | 0 | HT and PP Governor LW | Complete
|  | 1.1.4 | Governor visit to monitor the amount of time of PP and non PP time spent with the teacher in classes. Report written | ZL,LW | 2021-09-14 | 2021-09-14 | 0 | HT and Governor LW | Complete
|  | 1.1.5 | Governor visit to monitor the amount of time of PP and non PP time spent with the teacher in classes | ZL,LW | 2022-02-01 | 2022-02-01 | 0 | HT and Governor LW
|  | 1.1.6 | Governor visit to monitor the amount of time of PP and non PP time spent with the teacher in classes | ZL,LW | 2022-05-01 | 2022-05-01 | 0 | HT and Governor LW
|  | 1.1.7 | Autumn P.P meetings are held, professional conversations are had surrounding children. Intervention groups identified. Covid Recovery money allocated to support | Catherine Caldwell/ZL | 2021-11-15 | 2021-11-15 | 175 | Pupil progress meetings on 15/11/21 |  | Catherine Caldwell's contribution is to moderate standards to ensure that they are in line with national standards.
|  | 1.1.8 | Spring P.P meetings are held well professional conversations are hard surrounding children. Intervention groups identified | Catherine Caldwell/ZL | 2022-03-15 | 2022-03-15 | 175 | Pupil progress meetings on 15/03/21
|  | 1.1.9 | Summer P.P meetings are held well professional conversations are hard surrounding children. Intervention groups identified | Catherine Caldwell/ZL | 2022-06-28 | 2022-06-28 | 175 | Pupil progress meetings on 28/06/22
|  | 1.1.10 | Discussions over final targets and discussions re. setting new ones | LL,AH,HF,HC | 2022-06-28 | 2022-06-28 | 0 | Pupil progress meetings on 28/06/22
|  | 1.1.11 | Conversations are had between current and previous teacher to share information | LL,AH,HF,HC | 2021-07-01 | 2021-07-01 | 0 | All teachers | Complete
| 1.2 | 1.2.1 | Staff trained in the delivery of R, W, I phonics | Tiffany Prime | 2021-09-02 | 2021-09-02 | 1000 | AH- phonics observations | Complete
|  | 1.2.2 | Teachers and teaching assistants receive x4 additional RWI training sessions at Twilight staff meetings | AH | 2021-09-01 | 2021-09-29 | 0 | AH | Complete
|  | 1.2.3. | Wellcome assessments on Reception children to identify those needing more language support- follow up work in classroom | HS/CH | 2021-09-01 | 2022-07-01 |  | ZL | Green
|  | 1.2.3 | Reading INSET training for all staff 0.5 day October 22nd | Catherine Caldwell | 2021-10-22 | 2021-10-22 | 175 | AH,ZL
|  | 1.2.3 | Phonics lead to monitor the implementation of the R,W,I | AH/ZL/Amy Wells from hub | Sep | Ongoing | Time out of classroom | Book looks/planning - SLT | Green
|  | 1.2.4 | Phonics lead to work with the English hub to see if the school is on track in delivering R,W,I | AH/ZL/Amy Wells from hub | 2021-09-01 | Ongoing |  | AH
|  | 1.2.5 | Phnics lead checks the reading records for children in lowest 20% to see how they are progressing | AH,ZL | Sept 21, Dec 21, Feb 22, Marc 22, May 22 |  |  | ZL | Green
|  | 1.2.6 | Phonics book monitoring | AH | Nov | Ongoing | 0 | AH
|  | 1.2.7 | Support from the Read, Write, Inc representative | AH/ Tiffany from R,W,I | 2021-09-01 | 2022-07-01 | As part of cost of traning £k paid 2020 |  |  | Tiffany is booked to revisit on 7th December 2021
| 1.3 | 1.3.1. | Read, Write, Inc assessments carried out - new groupings set | AH | 2021-10-01 | 2021-10-01 | x1 day subject leadership time | AH | Complete
|  | 1.3.2 | Read, Write, Inc assessments carried out | AH | 2021-12-01 | 2021-12-01 |  | AH
|  | 1.3.3 | Read, Write, Inc assessments carried out | AH | 2022-02-01 | 2022-02-01 |  | AH
|  | 1.3.4 | Read, Write, Inc assessments carried out | AH | 2022-03-01 | 2022-03-01 |  | AH
|  | 1.3.5 | Read, Write, Inc assessments carried out | AH | 2022-05-01 | 2022-05-01 |  | AH
|  | 1.3.6 | Read, Write, Inc assessments carried out | AH | 2022-07-01 | 2022-07-01 | 0 | staff meeting minutes - SLT/Gov
| 1.4 | 1.4.1 | All staff to receive reading training on October INSET 0.5 day | Catherine Caldwell | 2021-10-22 | 2021-10-22 | 175 | AH,ZL |  | Catherine Caldwell is supporting the delivery of reading within our curriculum
|  | 1.4.2 | Reading volunteers trained in how to hear readers most effectively and delpoyed to classrooms | JP | 2021-09-27 |  | x1 Hour TA additional | ZL | Complete | Volunteers begin hearing children read in school week commencing 04/10/21
| 1.5 | 1.5.1 | Stimulating and engaging 'reading corners' will be set up in every classroom | LL,AH,HF,HC | 2021-09-01 |  | 0 |  | Complete
| 1.6 | 1.6.1 | Staff to read x3 times a week to class | AH | 2021-09-01 | Ongoing | 0 | AH/ZL | Green
|  | 1.6.2 | Staff to encourage free readers to select a range of challenging texts | LL,AH,HF,HC | Sep | Ongoing | 0 | AH/ZL
|  | 1.6.3 | Children to be confident to discuss the texts they have read and are reading a range of texts | AH | Dec | Ongoing | 0 | AH | Green
|  | 1.6.4 | Books in reading area to be made accessible and changed/rearranged often (ongoing) | LL,AH,HF,HC | Dec | Ongoing | 0 | Environment walks/phots - SLT/Gov | Green
| 1.7 | 1.7.1 | Reading events will be held across the whole school that promotes reading- feedback from summer reading etc | AH | Ongoing |  |  | AH | Green
QE2 | 2.1 | 2.1.1 | Subject lead to check planning for evidence of stretch and challenge- see Monitoring/ Assessment plan |  | 2021-10-01 | 2021-07-01
|  | 2.2.1 | Staff to be trained in 'Mastering number programme 'for maths- through Maths hub | LL, AH,HF | 2021-09-01 | On- going |  | AH | Complete
|  | 2.3.1 | Children in KS1 to take part in additional daily core number sessions as part of the 'Mastering number programme' | LL,AH,HF,HC | 2021-10-01 | 2021-07-01 |  | AH
|  | 2.4.1 | Subject lead to observe lessons, talk to children and look in books for stretch and challenge- See Monitoring/Assessment plan | AH | 2021-10-01 | 2021-07-01
|  | 2.4.2 | Subject lead to lead staff training at staff meeting- see Monitoring/ Assessment plan | AH | 2021-10-01 | 2021-07-01
QE3 |  | 3.1.1 | Staff set individual targets for each child | LL,AH,HF,HC | 2021-09-03 | 2021-09-17 | 0 | HT via the G drive | Complete
|  | 3.1.2 | Staff identify PP children in class and plan for teaching of them | LL,AH,HF,HC | 2021-09-01 | 2021-09-17 | 0 | HT and PP Governor LW | Complete
|  | 3.1.3 | Governor visit to monitor the amount of time of PP and non PP time spent with the teacher in classes | ZL,LW | 2021-09-14 | 2021-09-14 | 0 | HT and Governor LW | Complete
|  | 3.1.4 | Governor visit to monitor the amount of time of PP and non PP time spent with the teacher in classes | ZL,LW | 2022-02-01 | 2022-02-01 | 0 | HT and Governor LW
|  | 3.1.5 | Governor visit to monitor the amount of time of PP and non PP time spent with the teacher in classes | ZL,LW | 2022-05-01 | 2022-05-01 | 0 | HT and Governor LW
|  | 3.2.6 | Autumn P.P meetings are held, professional conversations are had surrounding children. Intervention groups identified | Catherine Caldwell/ZL | 2021-11-15 | 2021-11-15 | 0 | Pupil progress meetings on 15/11/21
|  | 3.1.7 | Spring P.P meetings are held well professional conversations are hard surrounding children. Intervention groups identified | Catherine Caldwell/ZL | 2022-03-15 | 2022-03-15 | 0 | Pupil progress meetings on 15/03/21
|  | 3.1.8 | Summer P.P meetings are held well professional conversations are hard surrounding children. Intervention groups identified | Catherine Caldwell/ZL | 2022-06-28 | 2022-06-28 | 0 | Pupil progress meetings on 28/06/22
|  | 3.1.9 | Discussions over final targets and discussions re. setting new ones | LL,AH,HF,HC | 2022-06-28 | 2022-06-28 | 0 | Pupil progress meetings on 28/06/22
|  | 3.1.10 | Conversations are had between current and previous teacher to share information | LL,AH,HF,HC | 2021-07-01 | 2021-07-01 | 0 | All teachers | Green
| 3.2 | 3.2.1 | Writing lead monitors writing in books and looks at planning on G drive. Feedback at staff meeting | ZL | 2021-10-04 | 2021-10-13 | 0 | ZL
|  | 3.2.2 | Writing lead monitors writing in books and looks at planning on G drive. Feedback at staff meeting | ZL | 2022-01-10 | 2022-01-17 | 0 | ZL
|  | 3.2.3 | Writing lead monitors writing in books and looks at planning on G drive. Feedback at staff meeting | ZL | 2022-05-02 | 2022-05-11 | 0 | ZL
|  | 3.2.4 | Whole school book looks within staff meetings to identify issues. Comparing PP and non PP children. Cross referencing English books versus topic books | LL,AH,HF,ZL | 13/01/2021, 8/12/21, 19/01/22, 111/05/22
|  | 3.2.5 | Y2 and Y6 staff to attend moderation sessions run by County through Keystone | AH,HF,HC | 2022-02-21 | 2022-05-23 | Supply cover | ZL
| 3.3 | 3.3.1 | Writing lead monitors staff teaching writing during book looks. | ZL | 2021-10-04 | 2021-10-13 | 0 | ZL
|  | 3.3.2 | Writing lead monitors staff teaching writing during book looks. | ZL | 2022-01-10 | 2022-01-17 | 0 | ZL
|  | 3.3.3 | Writing lead monitors staff teaching writing during book looks. | ZL | 2022-05-02 | 2022-05-11 | 0 | ZL
| 3.4 | 3.4.1 | Writing lead monitors resources used in writing
| 3.5 | 3.5.1 | Writing events to be held in school throughout the year to rise the profile of writing | ZL | 2021-09-01 | Ongoing |  | ZL
QE4 | 4.1 | 4.1.1 | Staff to undetake a review of their current provision and to identify where more bespoke opportunities can be planned to enhance the offer available | LL,HF, HC | 2021-11-01 | 2021-12-01 |  | ZL
|  | 4.1.2 | Staff to publish their edited progression maps to the website | LL,HF,HC | 2021-12-01 | 2021-12-01 |  | ZL
PA1 | 1.1 | 1.1.1 | Subject leaders to look at their progression maps and to identify areas where they can make the curriculum extend beyond the acdemic, vocational or technical | LL,AH,HF,LL | 2021-11-01 | 2022-01-01 |  | ZL
PA2 | 2.1 | 2.1.1. | Ensure all staff have a clear understanding of the SIAMS framework and their responsibilities within it, Spring | LL,AH,HF,HC and teaching assistants | 2022-03-01 | ongoing |  | ZL
|  | 2.1.2 | Ensure all staff have a clear understanding of the SIAMS framework and their responsibilities within it, Summer | LL,AH,HF,HC and teaching assistants | 2022-07-01 |  |  | ZL
|  | 2.1.3 | RE planning, teaching and books monitored | LL,AH,HF,HC | 04/10/21, 17/1/22, 20/6/22 |  |  | ZL
|  | 2.1.4 | Feedback on RE at staff meetings | ZL | 6/10/21, 2/2/22, 11/5/22 |  |  | ZL
|  | 2.1.5 | Introducton of Archbisop of York's Award for Y5 | HC/GJ | 2021-09-01 | 2022-07-01 |  | ZL
LM1 | 1.1 | 1.1.1 | Teaching staff to complete 2nd 1:1 sessions with Leann Lynch Equate re. Subject leadership. | Leann Lynch | 2021-09-01 | 2021-09-01 |  |  |  | Funded through remaining money Improvement strategy
|  | 1.1.2 | Draft subject leadership Action plans written | LL,AH,HF | 2021-07-01 | 2021-07-01 |  | ZL
|  | 1.1.3 | Subject leadership plans are returned to staff. Final version submitted. Used to create SDP | LL,AH,HF,HC | 2021-09-01 | 2021-09-10 |  | ZL
|  | 1.1.4 | Staff to complete Intent section to inform SEF | LL,AH,HF,HC | 2021-09-27 |  |  | ZL | Complete
|  | 1.1.5 | Staff to complete final 1:1 session with Leann Lynch | LL,AH,HF,HC | 2021-11-16 |  |  | ZL
| 1.2 | 1.2.1 | Staff understand roles through Performance Development meetings | LL,AH,HF,HC | 2021-09-20 | 2021-09-25
|  | 1.2.2 | Mid year staff Performance Development meetings | LL,AH,HF,HC | 2022-02-01 | 2022-02-05 |  | ZL
|  | 1.2.3 | Subject leads have good knowledge of their subject. Ensure curriculum plans/website up to date | LL,AH,HC | 2021-09-01 | Ongoing |  | ZL
|  | 1.2.4 | All staff given 5 Subject leadership days to manage workload from Sept to end of March | LL, AH,HC | 2021-09-01 | 2021-03-01 | x15 days supply
|  | 1.2.5 | Subject leads to identify staff training needs through monitoring including identifying their own training needs. Records kept of training undertaken | LL,AH,HC | 2021-09-01 | Ongoing |  | ZL
|  | 1.2.6 | Maths subject leader to engage with 3rd year of Maths hub- sustaining year | AH and Maths support teacher- Anita Coupland | 2021-09-01 | 2022-07-01 |  | ZL |  | Anita Coupland is the Assistant Maths hub lead working with AH during the sutaining year
|  | 1.2.7 | Science STEM training for Science subject lead | LL | 2021-09-01 | 2022-07-01 |  | ZL
|  | 1.2.8 | Laura Lill to begin NPQLT- linked to science leadership through Lead hub | LL | 2021-11-01 | 2022-11-01 | 895 | ZL |  | Funded through remaining money left from Improvement strategy
|  | 1.2.9 | Introduction to Primary Computing course | HC/GJ | 2021-10-04
| 1.3 | 1.3.1 | Subject leads lead and monitor staff meetings as per Monitoring/Assessment schedule. | LL,AH,HC | 2021-09-01 | 2022-07-01 | 35 | ZL
| 1.4 | 1.4.1 | Subject leads identify where staff need extra CPD throughoout the year and action | LL, AH, HF, HC | 2021-09-01 | 2021-07-01
| 1.5 | 1.5.1 | Subject leads to keep section on website updated | LL,AH,HF,HC | 2021-09-01 | Ongoing |  | ZL
LM2 | 2.1 | 2.1.1 | Establish half termly rota for displays | HF | 2021-09-01 | 2021-07-01 |  | HF | Complete
|  | 2.1.2 | Work with EYFS consultant Helen Rutherford on the development of the EYFS environment | LL, CH | 2021-07-01 |  |  |  |  | Helen Rutherford is supporting LL with the EYFS
|  | 2.1.3 | Follow up work in September on changes made | LL,CH | 2021-09-13 |  |  | Zl/Govs | Complete | Report from Helen Rutherford
|  | 2.1.4 | Monitoring of EYFS environment and implemtation of new EYFS framework throughout the year | ZL/HR | Ongoing |  |  | ZL/Govs |  | Helen Rutherford and Tamsin Caputa to look at EYFS enviroment
| 2.2 | 2.2.1 | Defined reading areas created within areas in the classrooms | LL,AH,HF,HC | 2021-09-01 | Ongoing |  |  | Green
| 2.3 | 2.3.1 | Maximise the use of the outdoor environment to enhance learning opportunites for all | ZL | 2021-09-01 | 2022-07-01
LM3 | 3.1 | 3.1.1 | Head teacher to attend initial briefing on the Kyra peer review programme | ZL | 2021-09-01 |  |  |  | Complete
|  | 3.1.2 | HT and x2 teaching staff to attend training day on Peer Review process | Zl, AH, LL | 2021-10-08 |  |  | ZL | Green
|  | 3.1.3 | Peer review cycle to begin with triad of schools | ZL,AH,LL | 2021-10-01 | 2022-07-01 |  | ZL/Govs | Green
|  | 3.1.4 | Peer review to focus on SDP priorities - Reading and stretch and challenge in maths | ZL | 2021-10-01 | 2022-07-01 |  |  | Green
NOA1 | 1.1 | 1.1.1 | HT and Senior Adminstrator to advertise Stay and Play visits for next year's intake. | ZL,TS | 2021-09-01 | 2022-04-01 |  | Govs | Green | 1st stay and play visit held. Individula appoinments made.
|  | 1.1.2 | HT to personally show new parents round the school and to meet with them to discuss a possible aplication to school | ZL | 2021-09-01 | 2022-04-01 |  | Govs | Green
| 1.2 | 1.2.1 | HT to explore the possibility of Forest Schools within the school environment | ZL | 2022-04-01
|  | 1.2..2 | Attendance on a Forest School course | TBC | TBC | 2023-07-01
|  | 1.2.3 | Development of outdoor area involving PTA, Parents etc | All staff | S | 2022-12-01
| 1.3 | 1.3 | Obtain costings for new whiteboards and factor into April budget | ZL | 2022-04-01

## Settings
Data to support the spreadsheet. Please do not touch.
Red
Amber
Green
Complete