## Cover page
Date: | 2023-09-01

## Priority areas incl.objecti
Swinderby All Saints
School Strategic Development Plan 2023 - 2024 |  | Milestones
OFSTED Area | Priority | by Dec | RAG | by April | RAG | by July | RAG | Objective
Quality of Education | QE1: To ensure that Early Reading is taught consistently well delivering successful outcomes for ALL | Staff are delivering phonics lessons effectively. Intervention programmes are in place |  | 80% of children are on track to pass PSC |  | 90% of children are on track to pass the PSC
QE1:1 To ensure each staff member fully understands the high priority given to early reading/ phonics through being a Wave 5 partner school
QE1:2 To ensure high quality phonics and reading is taught daily and consistently in all classes leading to above national outcomes
QE1:3 To ensure regular, robust assessments lead to high outcomes
QE1:4 To ensure staff are recently trained in the teaching of reading to a high standard
QE1:5 To ensure children have access to a exciting and stimulating and well resourced reading environment
QE1:6 To ensure children have access to age appropriate reading texts post phonics lessons
QE1:7 To ensure the profile of reading is raised across the school and is evident at all times
Quality of Education | QE2: To raise the profile of reading across the whole school to deliver high outcomes for ALL pupils | Reading is evident across school in classrooms and around school |  | 80% of the children are on track with their reading |  | 90% of the children are on track with their reading
QE2:1 To ensure each member of staff sets aspirational targets related to reading
QE2:2 To ensure high quality reading is modelled and taught everyday
QE2:3 To ensure high quality texts are used
QE2:4 To ensure reading is celebrated and its profile raised across school throug reading events
Quality of Education | QE3: To improve outcomes in writing so that they are at least in line with national, both at EXS and GDS | Staff know from moderation what GDS looks like in their Year groups |  | Writing GDS is evident across the whole school in all year groups when assessed |  | Writing GDS in Years 2 and 6 is above the national average from 2023
QE3.1 To ensure each member of staff sets aspirational targets related to writing
QE 3.2 To ensure high quality writing is modelled and taught everyday
Q3.3 Staff to understand how to achieve greater depth writing through high quality teaching
Quality of Education | QE4: To ensure the curriculum meets the needs of the 1st 20% and the highest 20% | HT/SENDCO/Subject Leads report that this is being achieved |  | Children in the first 20% and highest 20% of needs are being met |  | Children in both the first 20% and highest 20% are making good progress from their starting points
Q4.1 : To ensure that staff follow the 'non negotiables' within the 'Teaching and Learning' policy
QE 4.2 To ensure that staff adapt the planned curriculum to meet the needs of the first 20% and the highest 20% of learners
QE 4.3 Subject leaders to monitor teaching using the non negotiables within the 'Teaching and Learning ' policy
QE 4.4 Subject leaders to triangulate evidence about their subject through observations, book looks, pupil voice etc.
Quality of Education | QE5: To ensure that SEN children make good progress from their starting points | SEN children's progress is monitored by the SENDCO following ISP reviews and assessment drops |  | SENCO to talk in detail about the progress of SEN children. B squared is being used |  | For 100% of SEN children to make good progress from their starting points
QE5.1 For the SENDCO to monitor attainment and progress of SEN children in lessons
Personal Development | PD1: To ensure that the curriculum successfully builds on pupils’ prior knowledge and that the learning for all pupils is skilfully adapted | All lessons are adapted and made bespoke to meet the needs of children |  | All non negotiables are being implemented into lessons |  | All children articulate the knowledge that they have learnt within their subjects
PD 1.1 Subject leaders to monitor teaching using the non negotiables within the 'Teaching and Learning ' policy
PD 1.2 Children to be given opportunities outside of curriculum subjects to develop skills
Personal Development | PD2: To ensure that the school is prepared for a SIAMS inspection this academic year | All staff aware of SIAMS framework |  | Staff gather the evidence needed for SIAMS |  | School has a successful SIAMS Inspection
PD 2.1 Leaders to ensure that SIAMS is given high priority in school
PD 2.2 Leaders to ensure that staff are mindful of SIAMS at all times
Behaviour and Attitudes | To ensure the curriculum meets the needs of the 1st 20% and the highest 20% | HT/SENDCO/Subject Leads report that this is being achieved |  | Children in the first 20% and highest 20% of needs are being met |  | Children in both the first 20% and highest 20% are making good progress from their starting points
BA 1.1 To ensure that staff adapt the planned curriculum to meet the needs of the first 20% and highest 20% of learners
BA 1.2 Staff to understand that behavuour is everyone's responsibility
Leadership & Management | LM1: Leaders ensure that new subject leaders are equipped to lead their subjects well | Subject Leads have been trained in leading their subject |  | Subject Leads monitor their subjects in line with the Assessment/Monitoring plan |  | Subject leads undertaken a successful Ofsted inspection
LM 1.1 Staff to receive training on expectations within a maths lesson
LM 1.2 All teaching staff to understand the role of subject leads
Leadership & Management | LM2: Leaders to build a strong new team | The team are all fulfiling their roles effectively |  | Subject Leads suggest areas to improve |  | Subject leads create subject leadership action plans for the next acdemic year
LM 2.1 Leaders to build a strong team with a common goal
Early Years | To ensure that EYFS provision meets the needs of pupils | EYFS provision working well |  | EYFS provision being adapted to meet current needs |  | EYFS outcomes are ablove national
EYFS 1 .1 Ensure that the EYFS curriculum is planned and matched to the rest of the curriculum
EYFS 1.2 To ensure that the early years environment meets learners needs

## Actions
Objective Ref | Action Ref. | Action | Start date | Finish date | Costs | Who does | Who leads | Success criteria | Leader's RAG Rating | Monitor by | Monitor by RAG Rating | Narrative/comments
QE 1.1 | QE 1.1.1 | Staff to be familiarised with how being a Wave 5 school works | 2023-09-01 | 2026-07-01 | None | Phonics Lead | Phonics Lead | Is consistency seen across all phonics teaching |  | HT |  | This priority will continue into 23-24.
QE 1.1 | QE 1.1.2 | 6 visits Literacy Development days a year carried out by Reading Support Lead from Hub | 2023-09-01 | 2024-07-01 | None | Phonics Lead/Literacy Specialist | Phonics lead | Following Literacy Development days are processes improving? |  | HT/ Govs |  | Staff completed these in September '22
QE 1.2 | QE 1.2.1 | Weekly monitoring of the teaching of phonics | 2023-03-01 | Ongoing | Cover time for Phonics Lead | Phonics Lead/ HT | Phonics Lead | Is the teaching of phonics consistent across the school |  | HT/ Govs |  | Staff monitor these readers and prioritise them
QE 1.2 | QE 1.2.2 | Staff receive bespoke CPD linked to need | 2023-03-01 | Ongoing | None | Phonic Lead | Phonics Lead | Improvements are noted in delivery of lessons |  | HT/Govs |  | PP discussions are held at staff and Governor meetings
QE 1.3 | QE 1.3.1 | Half termly assessments for progress carried out - Oct/Dec/Feb/Apr/May/Jul | 2023-09-01 | 2024-07-01 | Cover for Phonics Lead | Phonics Lead | Phonics Lead | Children progressing at expected rates |  | HT |  | Atutum term meeting has been held with the HT and PP Governor to look at PP strategy and to discuss impact and spending plans for School Led recovery money
QE 1.3 | QE 1.3.2 | Interventions in place for children not making expected progress | 2023-09-01 | 2024-07-01 |  | TA responsible for Phonics intervention | Phonics Lead | Children making accelerated progress |  | HT
QE 1.4 | QE 1.4.1 | Staff receive 'Speed Sounds' training in September | 2023-09-04 | 2023-09-04 | Funded by English Hub | RWI Consultant- Tiffany Prime | Phonics Lead | Staff knowledgeable about what they are teaching |  | HT |  | PP data will be analysed at the end of the school year
QE 1.4 | QE 1.4.2 | Ongoing availability of and directed staff training via the RWI portal | 2023-03-01 | Ongoing |  | Phonics Lead | Phonics Lead | Quality of teaching is excellent |  | HT
QE 1.4 | QE 1.4.3 | Weekly staff training sessions held with staff and Phonics Lead | 2023-06-01 | Ongoing |  | Phonics Lead | Phonics Lead | Staff are more confident in their delivery |  | HT
QE 1.5 | QE 1.5.1 | Library books to be sorted and tidied | 2023-07-01 | 2024-07-01 |  | Phonics Lead/ HT | Phonics Lead/HT | Wider selection of books available for all to use |  | HT
QE 1.5 | QE 1.5.2 | Library revamp to be carried out on INSET day 30.10 23 | 2023-10-30 |  |  | All staff | HT | Library looks more inviting to use |  | HT
QE 1.5 | QE 1.5.3 | FOSS to begin fundraising for the School library revamp | 2023-09-01 | Ongoing |  | FOSS | HT | Library is modernised and revamped |  | HT
QE 1.5 | QE 1.5.4 | All staff to have an engaging Reading Corner with exciting books | 2023-09-01 | 2024-07-01 |  | Teaching staff | Phonics Lead | Children use the Reading Corners in their classrooms |  | HT
QE 1.6 | QE 1.6.1 | All children to receive a 30 mins taught reading session every day | 2022-09-01 | Ongoing |  | Teaching staff | Phonics Lead | Reading attainment increases |  | HT/Govs
QE 1.6 | QE 1.6.2 | Children to have an ongoing class story book(s) read to them at least x3 times a week | 2023-09-01 | 2024-07-01 |  | Teaching staff | Phonics Lead | Children are able to talk about their reading choices |  | HT
QE 1.7 | QE 1.7.1 | Children see and hear about books at all times- through Book Fairs, Events, Celebrations assembly etc | 2023-09-01 | 2024-07-01 |  | Teaching staff | Phonics lead | Children talk about reading |  | HT
QE 1.7 | QE 1.7.2 | The school is part of the Reading Pledge at the English Hub | 2023-09-01 | 2024-07-01 |  | All staff | Phonics Lead | The school achieves at least the Bronze award |  | HT
QE 2.1 | QE 2.1.1 | Teaching staff use FFT Aspire data to set aspirational targets in reading | 2023-09-01 | 2023-09-01 |  | Teaching staff | HT | Staff are familiar with the targets and how to work towards them |  | HT
QE 2.1 | QE 2.1.2 | Assessments check children against these targets at a miniumum of x3 times a year | Nov/March 23 Jun 24 | 2024-07-01 |  | Teaching staff | HT | Reading data is improving |  | HT
QE 2.2 | QE 2.2.1 | All children to receive a 30 mins taught reading session every day | 2022-09-01 | 2024-07-01 |  | Teaching staff | Phonics Lead | Reading attainment increases |  | HT
QE 2.3 | QE 2.3.1 | Reading spine is used by all staff. Specific books are non negotiable for each year group | 2023-09-01 | 2024-07-01 |  | Teaching staff | Phonics staff | Children experience awell planned diet of texts |  | HT
QE 2.4 | QE 2.4.1 | Reading is celebrated at all times around school | 2023-09-01 | 2024-07-01 |  | ALL staff | Phonics Lead | Children talk about reading |  | HT
QE 2.5 | QE 2.5.1 | 2nd year of Reading Fluency programme to be implemented via the LEAD Hub | 2023-09-01 | 2024-07-01 |  | Donna Woodcock- EYFS/ Ria Lane- Y1/2 | Phonics Lead | Children's language development improved |  | HT
QE 3.1 | QE 3.1.1 | Teaching staff use FFT Aspire data to set aspirational targets in writing | 2023-09-01 | 2023-09-01 |  | Teaching staff | Writing Lead | Staff are familiar with the targets and how to work towards them |  | HT
QE 3.2 | QE 3.2.1 | Years R to 2 taught writing daily through 'Get Writing' RWI | 2023-09-01 | Ongoing |  | Teaching staff | Writing Lead | KS1 children understand the structure of writing |  | HT
QE 3.2 | QE 3.2.2 | Staff to deliver daily modelled writing sessions | 2023-09-01 | 2024-07-01 |  | Teaching staff | Writing Lead | Children write confidently |  | HT
QE 3.2 | QE 3.2.3 | Staff attend writing moderation sessions throughout the year through Keystone to understand how they they can teach children how to improve their writing | 2023-09-01 | 2024-07-01 |  | Teaching staff | Writing Lead | Children know what is expected in their writing |  | HT
QE 3.3 | QE 3.3.1 | Staff know what greater depth writing looks like and aim for this through modelling and teaching from an earlier stage | 2023-09-01 | 2024-07-01 |  | Teaching staff | Writing Lead | Children use their reading knowledge to write at greater depth |  | HT
QE 3.3 | QE 3.3.2 | Use of moderation meetings with Catherine Caldwell x3 times a year | Nov/ Mar 23/ Jun 24 | 2024-07-01 |  | Catherine Caldwell | Writing Lead | Staff understand what the next steps are in children's learning |  | HT
QE 4.1 | QE 4.1.1 | Staff familarise themselves with Teaching and Learning Policy. All lessons are taught in line with this | 2023-09-01 | 2023-09-01 |  | Teaching staff | HT | Staff ensure all the components of a lesson are present |  | HT
QE 4.1 | QE 4.1.2 | Subject Leads to all receive new/refresher training on 'How to be a good subject leader' led by Catherine Stratton. | 2023-09-01 | 2023-12-01 | Staff meeting training cost | Catherine Stratton/HT | HT | Subject Leads understand what is required of them for Ofsted |  | HT
QE 4.1 | QE 4.1.3 | Subjects leaders work on a specific set of non negotiables for each of their subjects | 2023-09-01 | 2023-10-01 |  | Subject Leads | HT | Teachers know what is expected in each session |  | HT
QE 4.1 | QE 4.1.4 | Subject Leads use these non negotiables when they monitor their subject. See Monitoring/ Assessment Plan 23-24 | 2023-09-01 | 2024-07-01 |  | Teaching staff | HT | Subject Leads measure their success of the lessons they are monitoring through their non negotiables |  | HT
QE 4.2 | QE 4.2.1 | Staff follow the planned curriculum and make lessons bespoke and adpated to meet needs of first and highest 20% | 2023-09-01 | 2024-07-01 |  | Teaching staff | HT | Staff plans on curriculum show adaptations are taking place |  | HT
QE 4.2 | QE 4.2.2 | Staff all using the online Curriculum Maestro timetable to ensure all subjects are covered | 2023-09-01 | 2023-10-01 |  | Teaching staff | HT | Staff use the timetable online |  | HT
QE 4.2 | QE 4.2.3 | Staff teach to the highest level and scaffold the lesson for all children | 2023-09-01 | 2024-07-01 |  | Teaching staff | HT | Staff meet the needs of first and highest 20% of learners |  | HT
QE 4.3 | QE 4.3.1 | Subject Leaders to follow the Monitoring/ Assessment Plan 23-24 focussing on ensuring staff are using the non negotiables in their teaching | 2023-09-01 | 2024-07-01 |  | Subject Leads | HT | Staff meet the needs of first and highest 20% of learners |  | HT/Govs
QE 4.4 | QE 4.4.1 | Evidence gathered about their subjects through a combination of observations,book looks, pupil voice etc. | 2023-09-01 | 2024-07-01 |  | Subject Leads | HT | Assessment/ monitoring plan used effectively so that Subject Leads feel confident that subjects are being taught effectively |  | HT
QE 5.1 | QE 5.1.1 | SENDCO to carry out lesson observations of SEN children to see if their needs are being met | 2023-09-01 | 2024-07-01 |  | SENDCO | HT | Children with SEN are accessing the learning |  | HT
QE 5.1 | QE 5.1.2 | School to be involved in the Lincolnshire SEND Project- through training at LEARN | 2023-09-01 | 2024-07-01 |  | HT/SENDCO, Middle Leaders, Teachers and Teaching Assistants | HT | Staff deliver the highest SEN provision |  | HT/Govs
QE 5.1 | QE 5.1.3 | School to undergo a full SEN Review | 2023-12-01 | 2023-12-01 |  | HT/SENCO | HT | Action plan for SEN provision to be written |  | HT/Govs
QE 5.1 | QE 5.1.4 | SENDCO to monitor the assessment and progress of SEN children at the x3 assessment points in the year. Nov/ March/ June | 2023-11-01 | 2024-06-01 |  | SENDCO | HT | SEN children are making good progress from their starting points |  | HT/Govs
PD 1.1 | PD 1.1 | Subject Leaders to monitor non negotiables and to identify if learning needs are being met leading to positive behaviour and good levels of engagement | 2023-09-01 | 2024-07-01 |  | Subject Leads | HT | Behaviour is good in lessons Engagement levels are high |  | HT
PD 1.2 | PD 1.2 | Children throughout the school are encouraged to take part in extra curricular activities and develop other skills e.g leadership, mentoring etc | 2023-09-01 | 2024-07-01 |  | Teaching staff | HT | Children articulate opportunities outside of the classroom |  | HT
PD 2.2 | PD 2.1 | Staff to be briefed on the format of the anticipated SIAMS Inspection for 23-24 | 2023-09-01 | 2023-09-01 |  | All staff | RE Lead | Staff understand the SIAMS inspection |  | HT/SIAMS Govs
PD 2.2 | PD 2.1 | HT/RE Lead to collate evidence of SIAMS criteria in school | 2023-09-01 | 2023-12-01 |  | RE Lead/HT | HT | Evidence is gathered for SIAMS throughout school |  | HT/SIAMS Govs
BA 1.1 | BA 1.1.1 | Staff trained on meeting the first and highest 20% of needs | 2023-09-01 | 2023-09-01 |  | HT | HT | Staff know the children who are the first 20% and the highest 20% |  | HT
BA 1.2 | BA 1.2.1 | Staff receive INSET training on behaviour management for within school | 2023-09-01 | 2023-09-01 |  | HT | HT | Staff see behaviour as something that everyone is responsible for |  | HT
LM 1.1 | LM 1.1.1 | Staff meeting to look at expectations within a maths lesson | 2023-09-06 | 2023-09-06 |  | Claire Fraser- Maths Hub consultant | HT | All staff know the expectations of a maths lesson |  | HT
LM 1.1 | LM 1.1.2 | School to work with Maths Hub for the next year. School to have 6 Development Days across the year working with the Maths Hub | 2023-09-01 | 2023-07-01 |  | Claire Fraser- Maths Hub consultant/HT | HT | HT knows that maths delivery is good |  | HT
LM 1.1 | LM 1.1.3 | School to move to using White Rose Maths Version 3 | 2023-09-06 | 2024-07-01 |  | Maths Lead | HT | All children in school being taught using WRM Version 3 |  | HT
LM 1.1 | LM 1.1.4 | KS2 to take part in the Fluency project for Multiplication and Division | 2023-09-01 | 2024-07-01 |  | Maths hub/ Maths Lead | HT | Numeracy fluency project underway |  | HT
LM 1.2 | LM 1.2.1 | Subject Leads to be newly/ retrained on expectations of Subject Lead | 2023-09-01 | 2023-10-01 |  | Catherine Stratton | HT | Subject leads understand role |  | HT
LM 1.2 | LM 1.2.2 | Subject Leads to focus on first 20% and highest 20% when carrying out lesson observations | 2023-09-01 | 2024-07-01 |  | Subject Leads | HT | HT has confidence that 1st 20% and highest 20% needs are being met |  | HT
LM 2.1 | LM 2.1.1 | INSET Day 4th September to focus on the Team and the journey ahead | 2023-09-04 | Ongoing |  | HT/Chair of Govs | HT | The Team start to work together |  | HT
EY 1.1 | EY 1.1.1 | Produce the EYFS long and medium term plan linked to the whole school curriculum | 2023-03-01 | 2023-07-01 |  | EYFS Teacher | HT | EYFS plan is being implemented |  | HT
EY 1.2 | EY 1.2.1 | Redesign the EYFS classroom to ensure it meets EYFS needs as opposed to a mixed age class | 2023-07-01 | 2023-09-01 |  | EYFS Teacher | HT | Classroom is meeting the learning needs of the EYFS |  | HT
EY 1.2 | EY 1.2.2 | Monitor how the environment is meeting the needs of the children. Adjust provision as necessary | 2023-09-01 | 2024-07-01 |  | EYFS Teacher | HT | The environment is adapted over the year as the children's needs evolve |  | HT

## Settings
Data to support the spreadsheet. Please do not touch.
Red
Amber
Green
Complete